## Sheet1
Appendix 1
LION INDUSTRIES CORPORATION BERHAD (415-D)
(Formerly known as LION LAND BERHAD)
(Incorporated in Malaysia)
Proposed Divestment Programme
(i) | Status of the Proposed Divestments
|  |  | Proposed | Completed | Subsequent to December 2002
|  |  | Divestment | Before | Concluded | Amount Received/to be Received (Jan-Dec03)
|  | Stages of the Assets to be Divested | Programme | December | Sales | Received in | Projected | Projected
|  |  | (Per GWRS) | 2002 | Total | Current Qtr | to Dec 03 | Full Year
|  |  | RM'million | RM'million | RM'million | RM'million | RM'million | RM'million
|  | By December 2002 |  |  |  | (a) | (b) | (a)+(b)
|  | Unlisted shares in pharmaceutical company | 2 | 2 | 0 | 0 | 0 | 0
|  | Unlisted shares in automotive company | 29.4 | 29.4 | 0 | 0 | 0 | 0
|  | Listed shares in financial services company | 2.5 | 0 | 0 | 0 | 2.5 | 2.5
33.8
By December 2003
Shares in unlisted companies, industrial land, office
|  | block and shoplots in Parade and shopping centre | 174.3 | 0 | 0 | 0 | 174.3 | 174.3
By December 2004
Shares in unlisted companies and shoplots in
|  | Parade and shopping centre | 45.4 | 0 | 0 | 0 | 0 | 0
By December 2005
|  | Shares in unlisted company, factories and apartment | 9.7 | 0 | 0 | 0 | 0 | 0
By December 2006
Shares in unlisted companies, commercial land,
residential land and shoplots in Parade and
|  | shopping centre | 278 | 0 | 0 | 0 | 0 | 0
|  | Total | 541.2 | 31.4 | 0 | 0 | 176.8 | 176.8
The Group will, if necessary, divest other assets which are not part of the Proposed Divestment Programme,
to redeem / repay the Bonds and USD Debts.
(ii) | Transactions completed during the quarter
There were no transactions completed during the quarter.
(iii) | Utilisation of the divestment proceeds received
This note is not applicable.
SC Conditions : i) A summary status report on the divestment programme setting out the stages and the total divestment proceeds of each stage. ii) A comparison between the value of the concluded sale and the proceeds received for each concluded sale (for quarter & current year) together with the projections for the full year. iii) Plans to overcome any projected shortfall.
SC Conditions : i) Details on the transactions which have been completed for the quarter, including gross & net divestment proceeds for each asset which has been sold including the estimated timing on the receipts of the divestment proceeds.
SC Conditions : i) Details on the utilisation of the divestment proceeds received.