## JUDGEMENT
MENTIGA CORPORATION BERHAD
(Company No 10289 - K and its Subsidiaries)
LIST OF MATERIAL LITIGATIONS OF THE GROUP AS AT 22 FEBRUARY 2013 .
SUMMONS ISSUED AGAINST MCB;
NO | PLAINTIFF / LAWYER : | DEFENDEN / LAWYER: | AMOUNT CLAIM / COURT: | REMARKS
1 | KEKWA KREATIF SDN. BHD. / | MESSRS VENDARGON & PARTNERS | RM 5,549,625.00 | OUT OF COURT SETTLEMENT
| RAJADEVAN & ASSOC. |  |  | FULL AND FINAL SUM RM 6.O MILLION PLUS
|  |  | KTN HIGH COURT | RM 100 K FOR LEGAL FEES.
| KEKWA CLAIM AGAINST MENTIGA IS FOR THE BALANCE |  | CIVIL SUIT NO; 22 - 5 - 2000 | SUM RM 3.0 MILLION AND RM 100 K HAS BEEN
| OF PAYMENT DUE FOR WORK DONE IN DEVELOPING |  |  | PAID ON 20.01.12.
| PUSAT PERANGINAN PULAU SIBU MERSING " VIA CONTRACT |  |  | THE BALANCE RM 3.O MILLION TO BE PAID
| NO MCB/UP/SC/C.130 YEAR 1996 PLUS INTEREST OF 4% PER |  |  | BY WAY OF 1.0 MILLION EVERY SIXTH MONTHS
| ANNUM FROM THE DATE OF JUDGEMENT UNTIL REALIZATION. |  |  | UNTIL FULL AND FINAL PAYMENT.
FIRST INSTALMENT PAYMENT OF RM 1.0 MILLION
WAS PAID ON 04.07 2012.
SECOND INSTALMENT PAYMENT OF RM 1.0 MILLION
WAS PAID ON 31/12/2012
THIRD AND FINAL INSTALMENT PAYMENT OF
RM1.0 MILLION WILL BE PAID ON 20/07/2013

## MCB SOMMONS
MENTIGA CORPORATION BERHAD
(Company No 10289 - K and its Subsidiaries)
LIST OF MATERIAL LITIGATIONS OF THE GROUP AS AT 22 FEBRUARY 2013.
SUMMONS ISSUES BY MCB
NO | PLAINTIFF / LAWYER : | DEFENDEN / LAWYER: | AMOUNT CLAIM / COURT: | REMARKS
1 | MAHINDAR & CO. | KUMPULAN PENAMBANG | RM8,380,132.00 | BASED ON THE FACTS AND DOCUMENTS
|  | (JOHORE) SDN. BHD. / |  | PRESENTED, THE SOLICITORS HANDLING
| MENTIGA IS CLAIMING FOR THE AMOUNT OF RM8,380,132.00 | REGINALD VALLIPURAM & CO. |  | THE CASE ARE OF THE OPINION THAT
| IN RESPECT OF THE FOLLOWING; | (JOHOR BAHRU). |  | MENTIGA HAS A GOOD CLAIM.
| a) BALANCE OF PROGRESS PAYMENT |  |  | HARANAY,HISYAM,ANIKAH & ASSOCIATES
| FOR WORK DONE IN CONSTRUCTING |  |  | HAS WRITTEN TO PAM (PERSATUAN ARKITEK
| A RESORT IN PULAU SIBU RM1,744,606.14 |  |  | MALAYSIA) ON 09.01.2008 AND PAM HAS
CONFIRMED THAT THE ARBITRATION IS STILL
| b) RETENTION SUM RM1,292,532.96 |  |  | PENDING VIDE PAM SUIT NO : 499.
| c) CLAIM FOR VARIATION ORDER RM3,500,000.00 |  |  | A MEETING WAS HELD ON 27.04.2010
BETWEEN MCB AND THE TWO LAWYERS
| d) BALANCE SUM FOR ADDITIONAL |  |  | NAMELY DATO' MAHINDAR FROM MAHINDAR
| LANDSCAPE WORKS RM 213,520.10 |  |  | & CO AND EN HISYAM FROM HARANAY ,
HISHAM , ANIKAH & ASSOCIATES.
| e) CLAIM FOR RETURN OF MONEY |  |  | ISSUES RAISED DURING THE MEETING:-
WRONGFULLY DEDUCTED FROM
| THE PROGRESS CLAIMS RM 429,652.80 |  |  | a) TO ACT AND PROCEED IMMEDIATELY
WITH PAM.
| f) APPEAR FOR WAIVER OF LIQUIDATED |  |  | b) DISCUSSED ON THE SETTLEMENT
| AND ASCERTAINED DAMAGES RM1,200,000.00 |  |  | OF THE CURRENT OUTSTANDING AND
FUTURE FEES.
PAID TO MAHINDAR & CO RM 5,000.00
AND HARANAY,HISYAM,ANIKAH & ASS
RM 5,000.00 ON 28 JULY 2010.
RECEIVED NO CORPORATION FROM MESSRS
MAHINDAR & CO.TO DISCUSS WITH R.S.PANI
FOR FURTHER COURSE OF ACTION.